## GRID A-DET1
PROJECT: |  | Construction of Mixed-use Building | [7 empty] | DATE: |  | 2026-02-23
CONTRACTOR: |  | Main Contractor | [7 empty] | REF: No. |  | TR-01
CLIENT: |  | Client Project Management Team (Riyadh) | [7 empty] | DRAWING REF: |  | SD-ST-053-R01
BOLTED CONNECTION INSPECTION REPORT (GRID A) - LEVEL-02
Detail No. | Connection Description | Beam/Column | Beam/Column | Type of Connection (shear/moment) | Approximate Torque Value (N.m) | Plate (mm) |  |  | Bolts |  | Weld Size (mm) | Status | Remarks (deviation from approved drawings, deformation and/or protrusion)
[6 empty] | L | W | T | qty. | ø
1 | Beam to Column
1-a | Beam to Column | B-HEB400 | C-HEB220 | Moment | 476 | 230 | 230 | 20 | 9 | 20 | 10
1-b | Beam to Column | B-IPE300 | C-HEB220 | Moment | 476 | 350 | 160 | 15 | 8 | 20 | 10
|  | B-IPE300 | C-HEB220 | Moment | 476 | 200 | 175 | 15 | 6 | 20 | 10
1-c | Beam to Column | B-IPE300 | B-HEB400 | Moment | 476 | 230 | 230 | 20 | 9 | 20 | 10
|  | B-IPE300 | C-HEB220 | Moment |  | 187 | 105 | 10 |  |  | 10
|  | B-IPE300 | C-HEB220 | Moment |  | 187 | 105 | 10 |  |  | 10
DETAIL -1
Notes:
| PREPARED BY: | [8 empty] | APPROVED BY:
| SITE ENGINEER, STRUCTURAL / CIVIL | [8 empty] | SENIOR QA/QC INSPECTOR, STRUCTURAL / CIVIL
| Main Contractor | [8 empty] | Client Project Management Team
| 2026-02-23 | [8 empty] | 2026-02-23

## GRID A-DET2
PROJECT: |  | Construction of Mixed-use Building | [7 empty] | DATE: |  | 2026-02-23
CONTRACTOR: |  | Main Contractor | [7 empty] | REF: No. |  | TR-02
CLIENT: |  | Client Project Management Team (Riyadh) | [7 empty] | DRAWING REF: |  | SD-ST-054-R01
BOLTED CONNECTION INSPECTION REPORT (GRID A) - LEVEL-02
Detail No. | Connection Description | Beam/Column | Beam/Column | Type of Connection (shear/moment) | Approximate Torque Value (N.m) | Plate (mm) |  |  | Bolts |  | Weld Size (mm) | Status | Remarks (deviation from approved drawings, deformation and/or protrusion)
[6 empty] | L | W | T | qty. | ø
2 | Beam to Column
2-a | Beam to Column | B-IPE330 | C-HEB300 | Moment | 244 | 200 | 200 | 20 | 9 | 16 | 10
|  | B-IPE330 | C-HEB300 | Moment |  | 262 | 144 | 10 |  |  | 10
|  | B-IPE330 | C-HEB300 | Moment |  | 262 | 144 | 10 |  |  | 10
|  | B-IPE330 | C-HEB300 | Moment |  | 150 | 80 | 15 |  |  | 10
2-b | Beam to Column | B-IPE330 | C-HEB300 | Moment | 244 | 200 | 200 | 20 | 9 | 16 | 10
2-c | Beam to Column | B-IPE330 | C-HEB300 | Moment | 1634 | 680 | 280 | 20 | 10 | 30 | 10
DETAIL -2
Notes:
| PREPARED BY: | [8 empty] | APPROVED BY:
| SITE ENGINEER, STRUCTURAL / CIVIL | [8 empty] | SENIOR QA/QC INSPECTOR, STRUCTURAL / CIVIL
| Main Contractor | [8 empty] | Client Project Management Team

## GRID A -DET1 BOLT TIGHT
PROJECT: |  | Construction of Mixed-use Building | [7 empty] | DATE: |  | 2026-02-23
CONTRACTOR: |  | Main Contractor | [7 empty] | REF: No. |  | TR-01
CLIENT: |  | Client Project Management Team (Riyadh) | [7 empty] | DRAWING REF: |  | SD-ST-053-R01
BOLTED CONNECTION INSPECTION REPORT (GRID A) - LEVEL-02
Mark No. | Detail No. | Torque Value (N.m) | Deformation |  | Torque Value |  | Protrusion |  | Average Torque Value | Status | Remarks
| 1 |  | Accept | Reject | Accept | Reject | Accept | Reject | (N.m)
1 | 1A | 476
2 |  | 476
3 |  | 476
4 |  | 476
5 |  | 476
6 |  | 476
7 |  | 476
8 |  | 476
9 |  | 476 | [6 empty] | 476
1 | 1B | 476
2 |  | 476
3 |  | 476
4 |  | 476
5 |  | 476
6 |  | 476
7 |  | 476
8 |  | 476 | [6 empty] | 476
1 | 1B (Cont.) | 476
2 |  | 476
3 |  | 476
4 |  | 476
5 |  | 476
6 |  | 476 | [6 empty] | 476
1 | 1C | 476
2 |  | 476
3 |  | 476
4 |  | 476
5 |  | 476
6 |  | 476
7 |  | 476
8 |  | 476
9 |  | 476 | [6 empty] | 476
Notes:
| PREPARED BY: | [8 empty] | APPROVED BY:
| SITE ENGINEER, STRUCTURAL / CIVIL | [8 empty] | SENIOR QA/QC INSPECTOR, STRUCTURAL / CIVIL
| Main Contractor | [8 empty] | Client Project Management Team

## GRID A -DET2 BOLT TIGHT
PROJECT: |  | Construction of Mixed-use Building | [7 empty] | DATE: |  | 2026-02-23
CONTRACTOR: |  | Main Contractor | [7 empty] | REF: No. |  | TR-02
CLIENT: |  | Client Project Management Team (Riyadh) | [7 empty] | DRAWING REF: |  | SD-ST-054-R01
BOLTED CONNECTION INSPECTION REPORT (GRID A) - LEVEL-02
Mark No. | Detail No. | Torque Value (N.m) | Deformation |  | Torque Value |  | Protrusion |  | Average Torque Value | Status | Remarks
| 2 |  | Accept | Reject | Accept | Reject | Accept | Reject | (N.m)
1 | 2A | 244
2 |  | 244
3 |  | 244
4 |  | 244
5 |  | 244
6 |  | 244
7 |  | 244
8 |  | 244
9 |  | 244 | [6 empty] | 244
1 | 2B | 244
2 |  | 244
3 |  | 244
4 |  | 244
5 |  | 244
6 |  | 244
7 |  | 244
8 |  | 244
9 |  | 244 | [6 empty] | 244
1 | 2C | 1634
2 |  | 1634
3 |  | 1634
4 |  | 1634
5 |  | 1634
6 |  | 1634
7 |  | 1634
8 |  | 1634
9 |  | 1634
10 |  | 1634 | [6 empty] | 1634
Notes:
| PREPARED BY: | [8 empty] | APPROVED BY:
| SITE ENGINEER, STRUCTURAL / CIVIL | [8 empty] | SENIOR QA/QC INSPECTOR, STRUCTURAL / CIVIL
| Main Contractor | [8 empty] | Client Project Management Team